## Project Timeline
PROJECT TIMELINE TEMPLATE
PROJECT TITLE |  | Pandas STock Analysis
PROJECT TEAM |  | Tracie B, Ariana F, Luan Ng, James Y, Brandon J
PHASE |  |  | DETAILS |  | P.I.C | Status | deliverables
PROJECT WORKING DAY:
DAY 1 & 2 | Project Conception and Initiation |  | - Project PROPPOSAL |  | all team | COMPLETED |  | PRESENT DAY
|  |  | - Github Repo Manager |  | Tracie
|  |  | - searching data sets |  | all team
|  |  | - Buy a domain for web |  | Tracie
|  |  | - agreed on data sets |  | all team
DAY 3 | Project detail Planning & Starting steps |  | - manipulating data |  | James ¦ Tracie | completed
|  |  | - HTML ¦ CSS draft (landing page) |  | Tracie | completed
|  |  | - HTML ¦ CSS develop more & complete |  | Luan | completed
|  |  | - Web direction ¦ Task list & timeline management |  | Tracie | completed
|  |  | - SQL database |  | Tracie | completed
DAY 4 | Deeper diving |  | - Plotting all line charts |  | Tracie | on-fixing
|  |  | - Plotting all bubble charts |  | Tracie | on-fixing
|  |  | - Plotting all boxplot |  | James | on-fixing
|  |  | - html ¦ css files for 3 content pages & link to landing pages |  | Tracie | completed
|  |  | - Flask ¦ Api |  | Luan | COMPLETED
DAY 5 | Fine-tune the web for presentation |  | fine-tune content (text) |  | Ariana | almost completed
|  |  | - Link all plot.js to html & css |  | Tracie ¦ Luan
|  |  | - polish ¦ finish the home page |  | Luan
- each member to send short bio & pic to Luan
|  |  | Tracie bio + pic |  |  | COMPLETED
|  |  | Luan bio + pic |  |  | COMPLETED
|  |  | Brandon bio + pc |  | pending
|  |  |  | James | pending
|  |  |  | Ariana |  | COMPLETED
|  |  | - Push all into github.io |  | James¦Luan¦Tracie
FINAL DAY | G-TIME: PRESENTATION |  | - Home page
- Data source page
- Industry 3 pages